**Evaluation Calendar for Vision Viksit Bharat @2047**

**The calendar is prepared to keep in view to declare the result by 10 August 2024**

**Schedule for Category A (Three Stages)**

Stage 1: Sorting and Screening of Applications

* **Total Applications: 4000**
* **Duration: 16 July - 22 July (7 days)**
* **Experts Needed per Day: 4000 / (7 \* 20) ≈ 29 experts**

**Back Office Preparations: 23 July - 24 July (2 days)**

Stage 2: Blind Evaluation of Proposals

* **Proposals for Evaluation: 4000**
* **Duration: 25 July – 2 August (9 days)**
* **Experts Needed per Day: 4000 / (9 \* 20) ≈ 23 experts**

**Back Office Preparations : 3 August – 4 August (2 days)**

Stage 3: Final Selection (Interaction)

* - **Proposals for Final Review: 800 application**
* **- Duration: 5 August - 8 August (4 days)**
* **- Experts Needed per Day: 800 / (4 \* 20) = 20 experts**

**\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\*\***

**Calendar for Category B (Four Stages)**

Stage 1: Sorting and Screening of Applications

* **- Total Applications: 300**
* **- Duration: 17 July - 19 July (3 days)**
* **- Experts Needed per Day: 300 = 6 experts**

**Back Office Preparations: 20 July - 21 July (2 days)**

Stage 2: Blind Evaluation of Proposals

* - **Proposals for Evaluation: 200**
* **- Duration : 22 July - 25 July (4 days)**
* **- Experts Needed per Day: 300 ≈ 6experts**

**Back Office Preparations: 26 July – 27**

**July (2 days)**

Stage 3: First Round of Interaction

* - **Applicants for Interaction: 100**
* **- Duration: 28 July - 29 July (2 days)**
* **- Experts Needed per Day: 100 / 2 = 50 applicants (3 experts) per day**

**Back Office Preparations: 30 July - 31 July (2 days)**

Stage 4: Second Round of Interaction and Final Selection

* - **Applicants for Interaction: 100**
* **- Duration: 1 August – 2 August (2 days)**
* **- Experts Needed per Day: 100/ 4 ≈ 25 applicants (8experts ) per day**

Final Result Declaration Date: 7-10 August

**Detailed Calendar for Evaluation and Declaration of Results by 10 August**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Category | Stage | Start Date | End Date | Duration | Experts Needed per Day |
| | Category A | Stage 1: Sorting and Screening | 16 July | 22 July | 7 days | 29 |
|  | Back Office Preparations | 23 July | 24 July | 2 Days | N/A |
|  | Stage 2: Blind Evaluation | 25July | 2August | 9 Days | 25 Experts |
|  | Back Office Preparations | 3 August | 4 August | 2 Days | N/A |
|  | Stage 3: Final Selection (Interaction ) | 5 August | 8 August | 4 Days | 20 experts |
|  | Back Office Preparations | 9 August | 10 August | 2Days | NA |
| Category B | Stage 1: Sorting and Screening | 17 July | 19 July | 3 Days | 5 |
|  | Back Office Preparations | 20 July | 21 July | 2 Days | N/A |
|  | Stage 2: Blind Evaluation | 22 July | 25 July | 4 days | 4 experts |
|  | Back Office Preparations | 26 July | 27 July | 2 Days | N/A |
|  | Stage 3: First Round of Interaction | 28 July | 29 July | 2 days | 6 experts |
|  | Back Office Preparations | 30 July | 31 July | 2 days | NA |
|  | Stage 4: Second Round of Interaction | 1 August | 2 August | 2 days | 6 experts |
|  | Back Office Preparation of Result | 3 August | 6 August | 4 Days | 2 Experts |

|